## EffortEstimation
Site | Category | Product | WP | WP-ID | Unit | Effort | Comment | Tuning Factor | Qty | Total | Role | Resource Category | Support Type | SPC | Rate | Cost | Resource Name | Start Date | End Date
Solution | DES | Solution | HLD medium complexity | DES-SOL-002 | Solution Level | 20 |  | 1 | 1 | 20 | SA | Internal | Onsite | JP | 428.25 | 8565 |  | 2026-03-30 | 2026-04-24
Lab | DES | CMG | CMG 1st node LLD (including CIQ) | DES-CMG-001 | per node | 15 | CMGa2-SMFx1 & CMGa2-UPF-Ux1 | 1 | 2 | 30 | Designer-CMG | Internal | Remote | IN | 144.86 | 4345.8 |  | 2026-04-13 | 2026-05-22
Lab | DES | CMG | CMG Subsequent LLD | DES-CMG-002 | per node | 5 | CMGa2-SMFx1 & CMGa2-UPF-Ux1 | 0.6 | 2 | 6 | Designer-CMG | Internal | Remote | IN | 144.86 | 869.16 |  | 2026-05-25 | 2026-06-01
Lab | I&I | CMG | CMG_I&I_MOP - Installation and Integration - VNF / CNF Onboarding - Method of Procedure Creation / Update | CO.PC.JP.102 | 1 x Node | 4 |  | 1 | 1 | 4 | SME-CMG | External | Onsite | JP | 233.64 | 934.56 |  | 2026-06-02 | 2026-06-05
Lab | I&I | CMG | CMG_ I&I_ EXEC - Installation and Integration - VNF / CNF Onboarding - MOP Execution (operator and checker) | CO.PC.JP.105 | 1 x Node | 3 | CMGa2-SMFx2 & CMGa2-UPF-Ux2 | 1 | 2 | 6 | SME-CMG | External | Onsite | JP | 233.64 | 1401.84 |  | 2026-06-08 | 2026-06-10
Lab | I&I | CMG | CMG_ I&I_INTG - Installation and Integration - System Element Integration: Northbound interfaces (operator and checker) | CO.PC.JP.111 | 1 x Node | 16 | CMGa2-SMFx2 & CMGa2-UPF-Ux2 | 1 | 2 | 32 | SME-CMG | External | Onsite | JP | 233.64 | 7476.48 |  | 2026-06-11 | 2026-07-02
Lab | TechMgmt | Solution | Site Manager | TM-Gen-011 | Site Level | 0.5 | CMGa2-SMFx2 & CMGa2-UPF-Ux2 | 1 | 16 | 8 | SA | Internal | Onsite | JP | 428.25 | 3426 | Site-Manager | 2026-06-11 | 2026-07-02
Lab | ATP | CMG | CMG Test Case List Creation (80 TC's) | ATP-CMG-001 | per product (80 TC's) | 2 | 160 Test Cases - 8 Weeks | 1 | 4 | 8 | SA | Internal | Onsite | JP | 428.25 | 3426 |  | 2026-04-27 | 2026-05-06
Lab | DES | CMG | CMG_DES_TDD- Design- Creation of Test Case Description Document including CLI and Expected Outputs | CO.PC.JP.114 | 80 x TCs | 20 | 160 Test Cases - 8 Weeks | 1 | 2 | 40 | SME-CMG | External | Onsite | JP | 233.64 | 9345.6 |  | 2026-05-07 | 2026-07-01
Lab | TechMgmt | Solution | SA support in phase with medium involvement | TM-Gen-002 | Project Level | 0.5 | ATP QA Support [8 Weeks] | 1 | 40 | 20 | SA | Internal | Onsite | JP | 428.25 | 8565 |  | 2026-07-02 | 2026-08-26
Production | DES | CMG | CMG Subsequent LLD | DES-CMG-002 | per node | 5 | CMGa2-SMFx16 & CMGa2-UPF-Ux16 | 0.6 | 32 | 96 | Designer-CMG | Internal | Remote | IN | 144.86 | 13906.56 |  | 2026-06-02 | 2026-10-13
Production | I&I | CMG | CMG_ I&I_ EXEC - Installation and Integration - VNF / CNF Onboarding - MOP Execution (operator and checker) | CO.PC.JP.105 | 1 x Node | 3 | CMGa2-SMFx16 & CMGa2-UPF-Ux16 | 1 | 16 | 48 | SME-CMG | External | Onsite | JP | 233.64 | 11214.72 |  | 2026-07-03 | 2026-08-05
Production | I&I | CMG | CMG_ I&I_INTG - Installation and Integration - System Element Integration: Northbound interfaces (operator and checker) | CO.PC.JP.111 | 1 x Node | 16 | CMGa2-SMFx16 & CMGa2-UPF-Ux16 | 1 | 16 | 256 | SME-CMG | External | Onsite | JP | 233.64 | 59811.84 |  | 2026-08-06 | 2027-02-01
Production | TechMgmt | Solution | Site Manager | TM-Gen-011 | Site Level | 0.5 | CMGa2-SMFx16 & CMGa2-UPF-Ux16 | 1 | 152 | 76 | SA | Internal | Onsite | JP | 428.25 | 32547 | Site-Manager | 2026-07-03 | 2027-02-01
Production | I&I | CMG | CMG_ I&I_ MOP - Installation and Integration - Configuration Change - Method of Procedure Creation / Update | CO.PC.JP.103 | 1 x Node | 2 | Small FNI | 1 | 1 | 2 | SME-CMG | External | Onsite | JP | 233.64 | 467.28 |  | 2027-02-02 | 2027-02-03
Production | I&I | CMG | CMG_ I&I_ EXEC - Installation and Integration - Configuration Change - MOP Execution (operator and checker) | CO.PC.JP.108 | 1 x Node | 3 | Small FNI | 1 | 1 | 3 | SME-CMG | External | Onsite | JP | 233.64 | 700.92 |  | 2027-02-04 | 2027-02-05
Production | TechMgmt | Solution | Site Manager | TM-Gen-011 | Site Level | 1 | Small FNI | 1 | 1 | 1 | SA | Internal | Onsite | JP | 428.25 | 428.25 | Site-Manager | 2027-02-04 | 2027-02-05
Production | ATP | CMG | CMG_F_BSM - Field activities, including ATP - Babysitting / System Monitoring (operator and checker) | CO.PC.JP.119 | 1 x Week | 10 | Small FNI - 1Week Monitoring | 1 | 1 | 10 | SME-CMG | External | Onsite | JP | 233.64 | 2336.4 |  | 2027-02-05 | 2027-02-11
Production | I&I | CMG | CMG_ I&I_ MOP - Installation and Integration - Configuration Change - Method of Procedure Creation / Update | CO.PC.JP.103 | 1 x Node | 2 | Large FNI | 1 | 1 | 2 | SME-CMG | External | Onsite | JP | 233.64 | 467.28 |  | 2027-02-12 | 2027-02-15
Production | I&I | CMG | CMG_ I&I_ EXEC - Installation and Integration - Configuration Change - MOP Execution (operator and checker) | CO.PC.JP.108 | 1 x Node | 3 | Large FNI | 1 | 1 | 3 | SME-CMG | External | Onsite | JP | 233.64 | 700.92 |  | 2027-02-16 | 2027-02-17
Production | TechMgmt | Solution | Site Manager | TM-Gen-011 | Site Level | 1 | Large FNI | 1 | 1 | 1 | SA | Internal | Onsite | JP | 428.25 | 428.25 | Site-Manager | 2027-02-16 | 2027-02-17
Production | ATP | CMG | CMG_F_BSM - Field activities, including ATP - Babysitting / System Monitoring (operator and checker) | CO.PC.JP.119 | 1 x Week | 10 | Large FNI - 1Week Monitoring | 1 | 1 | 10 | SME-CMG | External | Onsite | JP | 233.64 | 2336.4 |  | 2027-02-17 | 2027-02-23
Production | TechMgmt | Solution | SA support in phase with medium involvement | TM-Gen-002 | Project Level | 0.5 | FNI QA Support | 1 | 14 | 7 | SA | Internal | Onsite | JP | 428.25 | 2997.75 |  | 2027-02-04 | 2027-02-23
Solution | TechMgmt | General | SA support in phase with low involvement | TM-Gen-001 | Project Level | 0.25 |  | 1 | 107 | 26.75 | SA | Internal | Onsite | JP | 428.25 | 11455.6875 |  | 2026-08-27 | 2027-01-22
Solution | TechMgmt | General | TPM support in phase with medium involvement | TM-Gen-005 | Project Level | 0.5 |  | 1 | 237 | 118.5 | TPM | Internal | Onsite | JP | 428.25 | 50747.625 |  | 2026-03-30 | 2027-02-23
Solution | TechMgmt | General | TDL support in phase with low involvement | TM-Gen-007 | Project Level | 0.1 |  | 1 | 237 | 23.7 | TDL | Internal | Onsite | JP | 428.25 | 10149.525 |  | 2026-03-30 | 2027-02-23
[10 empty] | 857.95 | [5 empty] | 249051.8475
44580280.7025
Formulas:
End Date = WORKDAY([Start Date],[Total]-1)
End Date = WORKDAY([Start Date],[Total]/2-1)
Start Date = WORKDAY([Start Date, row above],10)
Start Date = WORKDAY([End Date, row above],1)
Note on M1: tc={006D0031-00C2-4B6D-A1E2-00DB005A00B1}: Reyes, Ivan (Nokia - JP/Tokyo): Internal External Central Subco
Note on N1: tc={00D800DA-0019-42F4-ACE2-005900F200A2}: Reyes, Ivan (Nokia - JP/Tokyo): Onsite Remote
Note on R1: tc={008300B6-008D-41F8-A30B-0077004100CD}: Reyes, Ivan (Nokia - JP/Tokyo): Internal External Central Subco

## AssumptionsExclussions
Phase | Type | Description
ATP | Exclusion | SB is responsible for the ToL and TD creation
ATP | Assumption | Nokia will have to review the ToL and TD documents provided by SB

## WP-Weekly (260105-2132)
Site | BP Phase | BP Work Package | BP Work Item | BP Role | WP | WP-ID | Comment | Role | Product | Resource Category | Support Type | SPC | Resource Name | Total | 2026W13 | 2026W14 | 2026W15 | 2026W16 | 2026W17 | 2026W18 | 2026W19 | 2026W20 | 2026W21 | 2026W22 | 2026W23 | 2026W24 | 2026W25 | 2026W26 | 2026W27 | 2026W28 | 2026W29 | 2026W30 | 2026W31 | 2026W32 | 2026W33 | 2026W34 | 2026W35 | 2026W36 | 2026W37 | 2026W38 | 2026W39 | 2026W40 | 2026W41 | 2026W42 | 2026W43 | 2026W44 | 2026W45 | 2026W46 | 2026W47 | 2026W48 | 2026W49 | 2026W50 | 2026W51 | 2026W52 | 2027W01 | 2027W02 | 2027W03 | 2027W04 | 2027W05 | 2027W06 | 2027W07 | 2027W08
Solution | RAD (I1 to I2) | CN PACO DESIGN | PACO HLD | Local SA | HLD medium complexity | DES-SOL-002 |  | SA | Solution | Internal | Onsite | JP |  | 20 | 4 | 5 | 5 | 5 | 1
Lab | RAD (I1 to I2) | CN PACO DESIGN | PACO LLD | Remote SA | CMG 1st node LLD (including CIQ) | DES-CMG-001 | CMGa2-SMFx1 & CMGa2-UPF-Ux1 | Designer-CMG | CMG | Internal | Remote | IN |  | 30 |  |  | 4 | 5 | 5 | 5 | 5 | 5 | 1
Lab | RAD (I1 to I2) | CN PACO DESIGN | PACO LLD | Remote SA | CMG Subsequent LLD | DES-CMG-002 | CMGa2-SMFx1 & CMGa2-UPF-Ux1 | Designer-CMG | CMG | Internal | Remote | IN |  | 6 | [8 empty] | 4 | 2
Lab | I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | CMG_I&I_MOP - Installation and Integration - VNF / CNF Onboarding - Method of Procedure Creation / Update | CO.PC.JP.102 |  | SME-CMG | CMG | External | Onsite | JP |  | 4 | [9 empty] | 3 | 1
Lab | I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | CMG_ I&I_ EXEC - Installation and Integration - VNF / CNF Onboarding - MOP Execution (operator and checker) | CO.PC.JP.105 | CMGa2-SMFx2 & CMGa2-UPF-Ux2 | SME-CMG | CMG | External | Onsite | JP |  | 6 | [10 empty] | 6
Lab | INT (I3 to I4) | CN PACO INTEGRATION AND VALIDATION | PACO INTEGRATION | Local SE | CMG_ I&I_INTG - Installation and Integration - System Element Integration: Northbound interfaces (operator and checker) | CO.PC.JP.111 | CMGa2-SMFx2 & CMGa2-UPF-Ux2 | SME-CMG | CMG | External | Onsite | JP |  | 32 | [10 empty] | 2 | 10 | 10 | 10
Lab | RAD (I1 to I2) | CN PACO DESIGN | PACO SYSTEM VALIDATION STRATEGY | Local SA | Site Manager | TM-Gen-011 | CMGa2-SMFx2 & CMGa2-UPF-Ux2 | SA | Solution | Internal | Onsite | JP | Site-Manager | 8 | [10 empty] | 0.5 | 2.5 | 2.5 | 2.5
Lab | RAD (I1 to I2) | CN PACO DESIGN | PACO HLD | Local SA | CMG Test Case List Creation (80 TC's) | ATP-CMG-001 | 160 Test Cases - 8 Weeks | SA | CMG | Internal | Onsite | JP |  | 8 |  |  |  |  | 4 | 4
Lab | ACC (I4 to I5) | CN PACO ACCEPTANCE | PACO ACCEPTANCE TEST | Local SE | CMG_DES_TDD- Design- Creation of Test Case Description Document including CLI and Expected Outputs | CO.PC.JP.114 | 160 Test Cases - 8 Weeks | SME-CMG | CMG | External | Onsite | JP |  | 40 | [5 empty] | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4
Lab | RAD (I1 to I2) | CN PACO DESIGN | PACO HLD | Local SA | SA support in phase with medium involvement | TM-Gen-002 | ATP QA Support [8 Weeks] | SA | Solution | Internal | Onsite | JP |  | 20 | [13 empty] | 0.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2
Production | RAD (I1 to I2) | CN PACO DESIGN | PACO LLD | Remote SA | CMG Subsequent LLD | DES-CMG-002 | CMGa2-SMFx16 & CMGa2-UPF-Ux16 | Designer-CMG | CMG | Internal | Remote | IN |  | 96 | [9 empty] | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3
Production | I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | CMG_ I&I_ EXEC - Installation and Integration - VNF / CNF Onboarding - MOP Execution (operator and checker) | CO.PC.JP.105 | CMGa2-SMFx16 & CMGa2-UPF-Ux16 | SME-CMG | CMG | External | Onsite | JP |  | 48 | [14 empty] | 10 | 10 | 10 | 10 | 8
Production | INT (I3 to I4) | CN PACO INTEGRATION AND VALIDATION | PACO INTEGRATION | Local SE | CMG_ I&I_INTG - Installation and Integration - System Element Integration: Northbound interfaces (operator and checker) | CO.PC.JP.111 | CMGa2-SMFx16 & CMGa2-UPF-Ux16 | SME-CMG | CMG | External | Onsite | JP |  | 256 | [18 empty] | 2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4
Production | RAD (I1 to I2) | CN PACO DESIGN | PACO SYSTEM VALIDATION STRATEGY | Local SA | Site Manager | TM-Gen-011 | CMGa2-SMFx16 & CMGa2-UPF-Ux16 | SA | Solution | Internal | Onsite | JP | Site-Manager | 76 | [14 empty] | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1
Production | I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | CMG_ I&I_ MOP - Installation and Integration - Configuration Change - Method of Procedure Creation / Update | CO.PC.JP.103 | Small FNI | SME-CMG | CMG | External | Onsite | JP |  | 2 | [44 empty] | 2
Production | I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | CMG_ I&I_ EXEC - Installation and Integration - Configuration Change - MOP Execution (operator and checker) | CO.PC.JP.108 | Small FNI | SME-CMG | CMG | External | Onsite | JP |  | 3 | [44 empty] | 1.5 | 1.5
Production | RAD (I1 to I2) | CN PACO DESIGN | PACO SYSTEM VALIDATION STRATEGY | Local SA | Site Manager | TM-Gen-011 | Small FNI | SA | Solution | Internal | Onsite | JP | Site-Manager | 1 | [44 empty] | 0.5 | 0.5
Production | Project Closure | CN PACO LAUNCH SUPPORT AND OJT | PACO INITIAL OPERATION SUPPORT | Local SE | CMG_F_BSM - Field activities, including ATP - Babysitting / System Monitoring (operator and checker) | CO.PC.JP.119 | Small FNI - 1Week Monitoring | SME-CMG | CMG | External | Onsite | JP |  | 10 | [45 empty] | 10
Production | I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | CMG_ I&I_ MOP - Installation and Integration - Configuration Change - Method of Procedure Creation / Update | CO.PC.JP.103 | Large FNI | SME-CMG | CMG | External | Onsite | JP |  | 2 | [46 empty] | 2
Production | I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | CMG_ I&I_ EXEC - Installation and Integration - Configuration Change - MOP Execution (operator and checker) | CO.PC.JP.108 | Large FNI | SME-CMG | CMG | External | Onsite | JP |  | 3 | [46 empty] | 3
Production | RAD (I1 to I2) | CN PACO DESIGN | PACO SYSTEM VALIDATION STRATEGY | Local SA | Site Manager | TM-Gen-011 | Large FNI | SA | Solution | Internal | Onsite | JP | Site-Manager | 1 | [46 empty] | 1
Production | Project Closure | CN PACO LAUNCH SUPPORT AND OJT | PACO INITIAL OPERATION SUPPORT | Local SE | CMG_F_BSM - Field activities, including ATP - Babysitting / System Monitoring (operator and checker) | CO.PC.JP.119 | Large FNI - 1Week Monitoring | SME-CMG | CMG | External | Onsite | JP |  | 10 | [46 empty] | 4 | 6
Production | RAD (I1 to I2) | CN PACO DESIGN | PACO HLD | Local SA | SA support in phase with medium involvement | TM-Gen-002 | FNI QA Support | SA | Solution | Internal | Onsite | JP |  | 7 | [44 empty] | 0.5 | 2.5 | 2.5 | 1.5
Solution | RAD (I1 to I2) | CN PACO DESIGN | PACO HLD | Local SA | SA support in phase with low involvement | TM-Gen-001 |  | SA | General | Internal | Onsite | JP |  | 26.75 | [21 empty] | 0.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 0.25
Solution | Project Level | CN PACO TECHNICAL MANAGEMENT | PACO TECHNICAL MANAGEMENT | Local TM | TPM support in phase with medium involvement | TM-Gen-005 |  | TPM | General | Internal | Onsite | JP |  | 118.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1.5
Solution | Project Level | CN PACO TECHNICAL MANAGEMENT | PACO DELIVERY MANAGEMENT | Remote TDL | TDL support in phase with low involvement | TM-Gen-007 |  | TDL | General | Internal | Onsite | JP |  | 23.7 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3

## BaseLine (260105-2132)
BP Phase | BP Work Package | BP Work Item | BP Role | Total [MWD] | Start Date | End Date
Project Level | CN PACO TECHNICAL MANAGEMENT | PACO TECHNICAL MANAGEMENT | Local TM | 120 | 2026-03-30 | 2027-02-23
Project Level | CN PACO TECHNICAL MANAGEMENT | PACO DELIVERY MANAGEMENT | Remote TDL | 23.7 | 2026-03-30 | 2027-02-23
RAD (I1 to I2) | CN PACO DESIGN | PACO HLD | Local SA | 90 | 2026-03-30 | 2027-02-23
RAD (I1 to I2) | CN PACO DESIGN | PACO SYSTEM VALIDATION STRATEGY | Local SA | 92.5 | 2026-06-11 | 2027-02-17
RAD (I1 to I2) | CN PACO DESIGN | PACO LLD | Remote SA | 142.5 | 2026-04-13 | 2026-10-13
I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | 68 | 2026-06-02 | 2027-02-17
INT (I3 to I4) | CN PACO INTEGRATION AND VALIDATION | PACO INTEGRATION | Local SE | 288 | 2026-06-11 | 2027-02-01
ACC (I4 to I5) | CN PACO ACCEPTANCE | PACO ACCEPTANCE TEST | Local SE | 40 | 2026-05-07 | 2026-07-01
Project Closure | CN PACO LAUNCH SUPPORT AND OJT | PACO INITIAL OPERATION SUPPORT | Local SE | 20 | 2027-02-05 | 2027-02-23

## Internal (260105-2132)
BP Phase | BP Work Package | BP Work Item | BP Role | Role | Support Type | SPC | Resource Name | Total [MWD] | 2026P04 | 2026P05 | 2026P06 | 2026P07 | 2026P08 | 2026P09 | 2026P10 | 2026P11 | 2026P12 | 2027P01 | 2027P02
Project Level | CN PACO TECHNICAL MANAGEMENT | PACO TECHNICAL MANAGEMENT | Local TM | TPM | Onsite | JP | TPM-Onsite-JP | 120 | 12.5 | 10 | 10 | 12.5 | 10 | 10 | 12.5 | 10 | 12.5 | 10 | 10
Project Level | CN PACO TECHNICAL MANAGEMENT | PACO DELIVERY MANAGEMENT | Remote TDL | TDL | Onsite | JP | TDL-Onsite-JP | 23.7 | 2.4 | 2 | 2 | 2.5 | 2 | 2 | 2.5 | 2 | 2.5 | 2 | 1.8
RAD (I1 to I2) | CN PACO DESIGN | PACO HLD | Local SA | SA | Onsite | JP | SA-Onsite-JP | 90 | 25 | 5 |  | 12.5 | 10 | 5 | 6.25 | 5 | 6.25 | 5 | 10
RAD (I1 to I2) | CN PACO DESIGN | PACO SYSTEM VALIDATION STRATEGY | Local SA | SA | Onsite | JP | Site-Manager | 92.5 |  |  | 10 | 12.5 | 10 | 10 | 12.5 | 10 | 12.5 | 10 | 5
RAD (I1 to I2) | CN PACO DESIGN | PACO LLD | Remote SA | Designer-CMG | Remote | IN | Designer-CMG-Remote-IN | 142.5 | 18.75 | 20 | 20 | 25 | 20 | 20 | 18.75

## External (260105-2132)
BP Phase | BP Work Package | BP Work Item | BP Role | Role | Product | WP | WP-ID | Qty | Effort | Total [MWD] | 2026P04 | 2026P05 | 2026P06 | 2026P07 | 2026P08 | 2026P09 | 2026P10 | 2026P11 | 2026P12 | 2027P01 | 2027P02
I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | SME-CMG | CMG | CMG_I&I_MOP - Installation and Integration - VNF / CNF Onboarding - Method of Procedure Creation / Update | CO.PC.JP.102 | 1 | 4 | 4 | bar: 2026P06
I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | SME-CMG | CMG | CMG_ I&I_ MOP - Installation and Integration - Configuration Change - Method of Procedure Creation / Update | CO.PC.JP.103 | 2 | 2 | 4 | 2027P02: 2
I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | SME-CMG | CMG | CMG_ I&I_ EXEC - Installation and Integration - VNF / CNF Onboarding - MOP Execution (operator and checker) | CO.PC.JP.105 | 18 | 3 | 54 | 2026P06: 2; 2026P07: 13; 2026P08: 3
I&C (I2 to I3) | CN PACO IMPLEMENTATION | PACO SW INSTALLATION | Local SE | SME-CMG | CMG | CMG_ I&I_ EXEC - Installation and Integration - Configuration Change - MOP Execution (operator and checker) | CO.PC.JP.108 | 2 | 3 | 6 | 2027P02: 2
INT (I3 to I4) | CN PACO INTEGRATION AND VALIDATION | PACO INTEGRATION | Local SE | SME-CMG | CMG | CMG_ I&I_INTG - Installation and Integration - System Element Integration: Northbound interfaces (operator and checker) | CO.PC.JP.111 | 18 | 16 | 288 |  |  | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 1
ACC (I4 to I5) | CN PACO ACCEPTANCE | PACO ACCEPTANCE TEST | Local SE | SME-CMG | CMG | CMG_DES_TDD- Design- Creation of Test Case Description Document including CLI and Expected Outputs | CO.PC.JP.114 | 2 | 20 | 40 | bar: 2026P05 to 2026P06
Project Closure | CN PACO LAUNCH SUPPORT AND OJT | PACO INITIAL OPERATION SUPPORT | Local SE | SME-CMG | CMG | CMG_F_BSM - Field activities, including ATP - Babysitting / System Monitoring (operator and checker) | CO.PC.JP.119 | 2 | 10 | 20 | 2027P02: 2